## Sheet1
Week | Task | Week
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Project Plan and Schedule
| Create Project Plan and Schedule that identifies specific team member, task and completion | J
Records activity in log book
Audio Playback and Recording
| Demonstrate Code to record playback audio to/from a buffer | H
| Ability to change playback and recording parameters programfmatically | H/J
Queue Functionality
| Choose a team members queue library to use, and demonstrate utility code to manipulate a queue of structures | Z
| Integrate the queue functionality and audio playback/recording into the Project code (make a simple menu) | H
Diagnostics
| Produce a short document identifying the diagnostics to be designed into the software | H
| Optional: Linux Based Software | N/A
| Team produces a Linux based version of the Software alongside the Windows implementation | N/A
2 | Project Status Report & Updated Project Plan / Schedule
| Submit updated project status report in standard format found in eConestoga |  | J
Submit updated Project Plan / Schedule
Records activity in log book
RS232 Communications
| Demonstrate code for simple RS232 communications (optionally / when necessary over virtual com ports) between two computers |  | Z
User Interface (Home) - Design
| Document a user interface design for the Home Station Software, including all planned user interactions (Optional: Home & Receiver stations may have the same design and students may use the provided Qt based GUI) |  | H/J
Proposed Screen design
Proposed set of user commands, descriptions, input/output and diagnostic test functions (may implement some)
Optional: Linux Based Software version
3 | Project Status Report & Updated Project Plan / Schedule
| Submit updated project status report in standard format found in eConestoga |  |  | J
Submit updated Project Plan / Schedule
Records activity in log book
User Interface (Receive) - Design
| Document a user interface design for the Receive Station Software, including all planned user interactions (Optional: Home & Receiver stations may have the same design and implementation) |  |  | J/H
Proposed Screen design
Proposed set of user commands, descriptions, input/output and diagnostic test functions (may implement some)
User Interface (Home) - Implementation
| Implement the user interface (top-level menu or equivalent) for the Home Station Software, including user interactions |  |  | Z/H
User interface includes the ability to send RS232 messages
User interface includes the ability to playback and record audio
User interface includes testing/diagnostic functions
| Function implemented showing that home RS232 transmissions can be received (to confirm transmission) |  |  | Z
4 | Project Status Report & Updated Project Plan / Schedule
| Submit updated project status report in standard format found in eConestoga |  |  |  | J
Submit updated Project Plan / Schedule
Records activity in log book
User Interface (Receive) - Implementation
| Implement and demonstrate the user interface for the Receive Station Software |  |  |  | Z/H
| User interface includes the ability to receive RS232 messages from the home station |  |  |  | Z
| User interface includes the ability to playback audio received |  |  |  | H
| User interface includes testing/diagnostic functions for sending a random Fortune Cookie |  |  |  | C
5 | Project Status Report & Updated Project Plan / Schedule
| Submit updated project status report in standard format found in eConestoga |  |  |  |  | J
Submit updated Project Plan / Schedule
Records activity in log book
Frame Design Documentation and Implementation
| Frame / Protocol design document developed and explained |  |  |  |  | H
| Demonstrate sending/receiveing of frames (messages preceded by a header) between home and receive stations |  |  |  |  | Z
| Ability to turn headers on and off for diagnostic purposes (sender must inform receiver if headers included/excluded) |  |  |  |  | Z
Queuing
| Demonstrate the Queueing of messages at the reciever (optionally at the transmitter as well) |  |  |  |  | Z
| Queued messages include the header information |  |  |  |  | H
| Demonstrate ability to report the number of messages in the Queue |  |  |  |  | H
Diagnostics
| Ability to send messages from the Fortune cookie file , print contents of a configuration file, etc. |  |  |  |  | Z
Compression - Text
| Demonstrate one or more compression algorithms (e.g. RLE, Huffman) running on a buffer (text only) |  |  |  |  | J
| Compression functionality is integrated with project code |  |  |  |  | J
6 | Project Status Report & Updated Project Plan / Schedule
| Submit updated project status report in standard format found in eConestoga | [5 empty] | J
Submit updated Project Plan / Schedule
Records activity in log book
Compression - Audio
| Demonstrate compression via RLE algorithm (minimum) (Huffman is optional) on an audio buffer | [5 empty] | J
Error Detection & Correction
| Demonstrate the sending and receiving of error detected and corrected messages (correction may be only on header info) | [5 empty] | H
Error detection on payload via checksum (as a minimum)
| Home and Receive Stations can turn on/off error detection/correction and compression | [5 empty] | Z
Phonebook at Receiver
| Demonstrate the manipulation of messages (insertion/display) in a phonebook (may use a Binary Tree or other data structure) | [5 empty] | Z
| Can display the IDs of the senders and the number of messages from that sender | [5 empty] | H
| Optional: Send/Receive encrypted data using Viginere/XOR cipher) | [5 empty] | J
7 | Final Project Status Report & Updated Project Plan / Schedule
| Submit updated project status report in standard format found in eConestoga | [6 empty] | J
Submit updated Project Plan / Schedule - Self Assessment of your Project's Completeness
Records activity in log book
Decompression
| Demonstrate decompression via RLE algorithm (minimum) (Huffman is optional) on an audio buffer | [6 empty] | J
Completed Project
| Demonstration and presentation of system operation that meets the MuSCoW requirements in the Project Charter | [6 empty] | J/H/Z
Completion of Shoulds depending on Project Team Size (e.g. Message Encryption using Viginere/XOR cipher, Broadcast capability, saved audio messages for replay later, robust error handling of the header information etc.)
Submission of Final Report including all Project Code / videos